## Sample Initial Backlog
Sample Initial Backlog
One, Estimated, Prioritized
Items closer to be developed should have less uncertainty…
Theme | Story | Story Points | Priority
Profiles | As a site member, I want to describe myself on my own page in a semi-structured way so that others can learn about me. That is, I can fill in predefined fields, but also have room for a free-text field or two. (It would be nice to let this free text be HTML or similar.) | 1 | 1
Profiles | As a site member, I can fill out an application to become a Certified Scrum Practitioner so that I can earn that designation. [Note: Certified Scrum Practitioner was the initial name of what became known as Certified Scrum Professional.] | 1 | 1
Profiles | As a Practitioner, I want my profile page to include additional details about me (i.e., some of the answers to my Practitioner application) so that I can showcase my experience. | 5 | 1
Profiles | As a site member, I can fill out an application to become a Certified Scrum Trainer so that I can teach CSM and CSPO courses and certify others. | 1 | 1
Profiles | As a Trainer, I want my profile page to include additional details about me (i.e., some of the answers to my Trainer application) so that others can learn about me and decide if I’m the right trainer for them. | 1 | 1
Profiles | As a Practitioner or Trainer, when I write an article for the site I want a small graphic shown with the article showing my CSP or CST status so that others know my certifications when reading. (For example, Amazon’s “Top 500 Reviewers” approach.) | 5 | 1
Profiles | As a trainer, I want my profile to list my upcoming classes and include a link to a detailed page about each so that prospective attendees can find my courses. | 5 | 1
Profiles | As a site member, I can view the profiles of other members so that I can find others I might want to connect with. | 1 | 1
Profiles | As a site member, I can search for profiles based on a few fields (class attended, location, name) so I can find others I might want to connect with. | 1 | 2
Profiles | As a site member, I can mark my profile as private in which case only my name will appear so that no one can learn things about me I don’t want shared. | 1 | 2
Profiles | As a site member, I can mark my email address as private even if the rest of my profile is not so that no one can contact me. | 5 | 2
Profiles | As a site member, I can send an email to any member via a form so that we can connect. | 8 | 2
Profiles | As a site administrator, I can read practicing and training applications and approve or reject them so that only applicants who qualify can become CSPs or CSTs. | 5 | 2
Profiles | As a site administrator, I can edit any site member profile so that I can correct problems for members. | 8 | 3
News | As a site visitor, I can read current news on the home page so that I stay current on agile news. | 13 | 3
News | As a site visitor, I can access old news that is no longer on the home page, so I can access things I remember from the past or that others mention to me. | 20 | 3
News | As a site visitor, I can email news items to the editor, so they can be considered for publication. (Note: this could just be an email link to the editor.) | 13 | 3
News | As a site a site editor, I can set the following dates on a news item: Start Publishing Date, Old News Date, Stop Publishing Date so articles are published on and through appropriate dates. These dates refer to the date an item becomes visible on the site (perhaps next Monday), the date it stops appearing on the home page, and the date it is removed from the site (which may be never). | 20 | 3
Resource | As a site member, I can download the latest training material and methodology PDFs so I have them. | 20 | 3
Resource | As a visitor, I can download presentations, PDFs, etc. on Scrum so that I can learn from them or use them. | 40 | 4
Jobs | As someone who wants to hire, I can post a help wanted ad so that I can attract candidates. | 80 | 4

## Scope changes
Scope changes
We track events that change the scope of the project, so we can provide early and frequent feedback about progress.
Sprint | Event description | Who requested the change | Points
1 | Initial project estimation | Mat (Product Owner) | 464
2 | Reduced scope due to… | Mat (Product Owner) | -50
4 | New requeriments were requested for … | Mat (Product Owner) | 80
6 | Complexity for … was re-estimated. | Mat (Product Owner) | -20
8 | Jobs module was re-designed and uncertainty is reduced | Mat (Product Owner) | -90
9 | New profiles module was added to the scope | Mat (Product Owner) | 200
10 | Uncertainty for thrid-party integration was reduced | Diana (Product Manager) | -55
12 | New integration with LinkedIn and new features were added | Mat (Product Owner) | 187
13 | Reduced scope due to… | Nev (Delivery Manager) | -12
17 | Reduced scope due to… | Diana (Product Manager) | -65
19 | Additional features for LinkedIn dashboard were added | Mat (Product Owner) | 58
Note on A4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: There may be several events per sprint.

## Team velocity
Team velocity
We track the delivery pace of the team.
Sprint | delivered points
1 | 51
2 | 54
3 | 46
4 | 53
5 | 36
6 | 18
7 | 23
8 | 35
9 | 30
10 | 42
11 | 40
12 | 26
13 | 32
14 | 16
15 | 24
16 | 20
17 | 26
18 | 26
19 | 17
20 | 39
21 | 27
22 | 16

## Burn Up Chart
Burn Up Chart
How the team delivers and how scope changes during the project

## Team capacity
Team capacity
We track who are the team members that contribute to the deliverables.
Sprint | # Team members | Days off | % Capacity | Absolute Capacity
1 | 7 |  | 100% | 7
2 | 7 |  | 100% | 7
3 | 7 | 8 | 88.57% | 6.2
4 | 7 | 2 | 97.14% | 6.8
5 | 7 | 7 | 90% | 6.3
6 | 7 | 17 | 75.71% | 5.3
7 | 7 | 35 | 50% | 3.5
8 | 6 | 13 | 78.33% | 4.7
9 | 6 | 1 | 98.33% | 5.9
10 | 6 | 3 | 95% | 5.7
11 | 6 | 8 | 86.67% | 5.2
12 | 5 | 10 | 80% | 4
13 | 5 | 0 | 100% | 5
14 | 5 | 18 | 64% | 3.2
15 | 4 | 5 | 87.5% | 3.5
16 | 4 | 10 | 75% | 3
17 | 5 | 6 | 88% | 4.4
18 | 5 | 1 | 98% | 4.9
19 | 5 | 11 | 78% | 3.9
20 | 5 | 1 | 98% | 4.9
21 | 4 | 1 | 97.5% | 3.9
22 | 4 | 15 | 62.5% | 2.5

## Sprints
Sprints
We estimate project duration based on Velocity and Future Capacity.
|  | How can we estimate Duration? |  | Points |  |  |  | Historic |  |  |  |  | Future
Sprint | Day 1 | Estimated Last Sprint with Historic Velocity | Estimated Last Sprint with Future capacity | In scope | Done in Sprint | Done overall | Remaining scope | Historic avg. velocity | Historic Team Member # | Historic capacity % | Historic Points per Person | Historic abs. Team Member | Future Team Member # | Future capacity % | Future abs. Team members | Estimated Future avg. Velocity
1 | 2020-06-01 | 10 | 13 | 464 | 51 | 51 | 413 | 51 | 7 | 100% | 7.2857 | 7 | 5.6364 | 85.83% | 4.8377 | 35.2461
2 | 2020-06-15 | 8 | 11 | 414 | 54 | 105 | 309 | 52 | 7 | 100% | 7.4286 | 7 | 5.5714 | 85.16% | 4.7444 | 35.2439
3 | 2020-06-29 | 9 | 11 | 414 | 46 | 151 | 263 | 50 | 7 | 96.19% | 7.4257 | 6.7333 | 5.5 | 84.41% | 4.6427 | 34.4756
4 | 2020-07-13 | 10 | 13 | 494 | 53 | 204 | 290 | 51 | 7 | 96.43% | 7.5556 | 6.75 | 5.4211 | 84.19% | 4.5642 | 34.4852
5 | 2020-07-27 | 11 | 13 | 494 | 36 | 240 | 254 | 48 | 7 | 95.14% | 7.2072 | 6.66 | 5.3333 | 83.47% | 4.452 | 32.0864
6 | 2020-08-10 | 12 | 14 | 474 | 18 | 258 | 216 | 43 | 7 | 91.9% | 6.6839 | 6.4333 | 5.2353 | 83.09% | 4.3501 | 29.0755
7 | 2020-08-24 | 12 | 14 | 474 | 23 | 281 | 193 | 40 | 7 | 85.92% | 6.6508 | 6.0143 | 5.125 | 83.55% | 4.282 | 28.4792
8 | 2020-09-07 | 10 | 11 | 384 | 35 | 316 | 68 | 39 | 6.875 | 84.97% | 6.6761 | 5.8417 | 5 | 85.79% | 4.2894 | 28.6369
9 | 2020-09-21 | 16 | 18 | 584 | 30 | 346 | 238 | 38 | 6.7778 | 86.46% | 6.4849 | 5.8597 | 4.9286 | 86.32% | 4.2544 | 27.5896
10 | 2020-10-05 | 14 | 16 | 529 | 42 | 388 | 141 | 38 | 6.7 | 87.31% | 6.496 | 5.8497 | 4.8462 | 85.4% | 4.1385 | 26.8837
11 | 2020-10-19 | 14 | 15 | 529 | 40 | 428 | 101 | 38 | 6.6364 | 87.25% | 6.5627 | 5.7903 | 4.75 | 84.6% | 4.0184 | 26.3713
12 | 2020-11-02 | 20 | 23 | 716 | 26 | 454 | 262 | 37 | 6.5 | 86.65% | 6.5696 | 5.632 | 4.6364 | 84.41% | 3.9135 | 25.71
13 | 2020-11-16 | 19 | 22 | 704 | 32 | 486 | 218 | 37 | 6.3846 | 87.67% | 6.6099 | 5.5976 | 4.6 | 84.85% | 3.9031 | 25.7992
14 | 2020-11-30 | 20 | 23 | 704 | 16 | 502 | 202 | 35 | 6.2857 | 85.98% | 6.4759 | 5.4046 | 4.5556 | 83.17% | 3.7887 | 24.5353
15 | 2020-12-14 | 21 | 22 | 704 | 24 | 526 | 178 | 35 | 6.1333 | 86.08% | 6.629 | 5.2798 | 4.5 | 85.56% | 3.8503 | 25.5237
16 | 2020-12-28 | 21 | 23 | 704 | 20 | 546 | 158 | 34 | 6 | 85.39% | 6.6361 | 5.1235 | 4.5714 | 85.29% | 3.8988 | 25.8727
17 | 2021-01-11 | 20 | 20 | 639 | 26 | 572 | 67 | 33 | 5.9412 | 85.54% | 6.493 | 5.0824 | 4.6667 | 87% | 4.06 | 26.3617
18 | 2021-01-25 | 20 | 20 | 639 | 26 | 598 | 41 | 33 | 5.8889 | 86.24% | 6.4981 | 5.0784 | 4.6 | 86.8% | 3.9928 | 25.9457
19 | 2021-02-08 | 22 | 23 | 697 | 17 | 615 | 82 | 32 | 5.8421 | 85.8% | 6.3838 | 5.0127 | 4.5 | 84% | 3.78 | 24.1306
20 | 2021-02-22 | 22 | 22 | 697 | 39 | 654 | 43 | 32 | 5.8 | 86.41% | 6.3847 | 5.012 | 4.3333 | 86% | 3.7267 | 23.7938
21 | 2021-03-08 | 22 | 22 | 697 | 27 | 681 | 16 | 32 | 5.7143 | 86.94% | 6.4411 | 4.9681 | 4 | 80% | 3.2 | 20.6117
22 | 2021-03-22 | 22 | 22 | 697 | 16 | 697 | 0 | 31 | 5.6364 | 85.83% | 6.408 | 4.8377 | 4 | 62.5% | 2.5 | 16.02
Formulas:
Day 1 = +WORKDAY([Day 1, row above],Parameters!$A5)

## Duration estimates
Duration estimates
Historic duration estimates based on scope changes, current velocity and future capacity during the project life-time.

## Parameters
Parameters
Yellow columns are calculated values.
DaysPerSprint
10